## Const. Plan
WW50 Construction Work Plan 06-12.12.20 V0.1
Row # | Discipline [OCS/Old Bridges/TS/SCADA & COM] | WW [Nº] | Date [DD/MM/YY] | T.P Start [Time] | T.P End [Time] | Work Description (Baseline) | Work Description
1 | TS | 50 | 2020-12-06 | 7:00 | 18:00 | construction | construction
2 | TS | 50 | 2020-12-06 | 7:00 | 18:00 | construction/electrical | construction/electrical
3 | TS | 50 | 2020-12-06 | 7:00 | 18:00 | construction | construction
4 | TS | 50 | 2020-12-06 | 7:00 | 18:00 | construction | construction
5 | TS | 50 | 2020-12-06 | 7:00 | 18:00 | construction | construction
6 | TS | 50 | 2020-12-06 | 8:00 | 18:00 | Laying water pipe parallel to ISR fence (inside ISR area) | construction
7 | OCS | 50 | 2020-12-06 | 8:00 | 17:00 | Open platforms in Hod Hasharon & Kfar Sava stations (Working on the platforms) | Open platforms in Hod Hasharon & Kfar Sava stations (Working on the platforms)
8 | OCS-D | 50 | 2020-12-06 | 8:00 | 17:00 | Marking on EP05 on Kp 73-69, All Tracks | Marking on EP05 on Kp 73-69, All Tracks
9 | SCADA&Comm | 50 | 2020-12-06 | 8:00 | 17:00 | Fix track vehicle in Pleshet on Track 3 | Fix track vehicle in Pleshet on Track 3
10 | SCADA&Comm | 50 | 2020-12-06 | 8:00 | 18:00 | LOD Depot Ring plastic tray installation | SCADA Pedestrian Team In LOD Depot
11 | OCS | 50 | 2020-12-06 | 18:00 | 5:00 | Erect poles on Kp 113-118, (Out of the track) | Special Solutions in Kp 113-118, (Out of the track)
12 | SCADA&Comm | 50 | 2020-12-06 | 21:00 | 5:00 | Ganey Aviv+K.Habad Rings works | SCADA Pedestrian Team In G.Aviv+ K.Habad
13 | SCADA&Comm | 50 | 2020-12-06 | 21:00 | 5:00 | Pleshet Ring plastic tray installation all tracks | SCADA Vehicle Team in Pleshet all tracks
14 | SCADA&Comm | 50 | 2020-12-06 | 21:00 | 5:00 | Ashdod Ring plastic tray installation all tracks | SCADA Pedestrian Team In Ashdod
15 | TS | 50 | 2020-12-07 | 7:00 | 18:00 | construction | construction
16 | TS | 50 | 2020-12-07 | 7:00 | 18:00 | construction/electrical | construction/electrical
17 | TS | 50 | 2020-12-07 | 7:00 | 18:00 | construction | construction
18 | TS | 50 | 2020-12-07 | 7:00 | 18:00 | construction | construction
19 | TS | 50 | 2020-12-07 | 7:00 | 18:00 | construction | construction
20 | TS | 50 | 2020-12-07 | 7:00 | 18:00 | construction | construction
21 | OCS | 50 | 2020-12-07 | 7:00 | 19:00 | Foundation EP07 - Kp 86 until Kp 89 Track 1+2 | Foundation EP07 - Kp 86 until Kp 89 Track 1+2
22 | OCS | 50 | 2020-12-07 | 7:00 | 19:00 | Foundation EP07 - Kp 2 until Kp 6 Track 1+2 | Foundation Activity with vehicle on Track Kp 2 until Kp 6, Track 1+2
23 | OCS | 50 | 2020-12-07 | 8:00 | 17:00 | RW on in LOD Depot | OCS Vehicle Activity in LOD Depot
24 | OCS | 50 | 2020-12-07 | 8:00 | 17:00 | Install Cantilevers in LOD Depot | OCS Vehicle Activity in LOD Depot
25 | OCS | 50 | 2020-12-07 | 8:00 | 17:00 | Open platforms in Hod Hasharon & Kfar Sava stations (Working on the platforms) | Open platforms in Hod Hasharon & Kfar Sava stations (Working on the platforms)
26 | OCS-D | 50 | 2020-12-07 | 8:00 | 17:00 | Marking on EP05 on Kp 73-69, All Tracks | Marking on EP05 on Kp 73-69, All Tracks
27 | SCADA&Comm | 50 | 2020-12-07 | 8:00 | 18:00 | LOD Depot Ring plastic tray installation | SCADA Pedestrian Team In LOD Depot
28 | OCS | 50 | 2020-12-07 | 18:00 | 5:00 | Erect poles on Kp 113-118, (Out of the track) | Special Solutions in Kp 113-118, (Out of the track)
29 | OCS | 50 | 2020-12-07 | 19:00 | 5:00 | Foundation EP07 - Kp 2 until Kp 6 Track 1+2 | Foundation Activity with vehicle on Track Kp 2 until Kp 6, Track 1+2
30 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | Foundation EP08 - Kp 118 until Kp 130, Track 1+2 | Foundation Activity with vehicle on Track Kp 118 until Kp 130, Track 1+2
31 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | Foundations on Kp 106-108, Tracks 1&2 | Foundation Activity with vehicle in Kp 106-108, Tracks 1&2
32 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | E&B on Kp 11-12, Tracks 1&2 | OCS Pedestrian Activity on Kp 11-12, Tracks 1&2
33 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | Foundations on Kp 3-4, Tracks 2&3&4&5&6 | Foundation Activity with vehicle on Kp 3-4, Tracks 2&3&4&5&6
34 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | Adjustments on Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
35 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | Install Droppers on Kp 131-133, Track 2 | OCS Vehicle Activity Kp 131-133, Track 2
36 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | Wiring OCS on KP 140-135, Track 1 | OCS Vehicle Activity KP 140-135, Track 1
37 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | Install cantilevers on Kp 134, Tracks 1&2 | OCS Vehicle Activity Kp 131-133, Track 2
38 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | Install droppers and F.O Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
39 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | Install cantilevers on Kp 16-18, Tracks 1&2 | OCS Vehicle Activity Kp 16-18, Tracks 1&2
40 | OCS | 50 | 2020-12-07 | 21:00 | 5:00 | Install RW on Kp 15-18, Tracks 1&2 | OCS Vehicle Activity Kp 15-18, Tracks 1&2
41 | SCADA&Comm | 50 | 2020-12-07 | 21:00 | 5:00 | Ganey Aviv+K.Habad Rings works | SCADA Pedestrian Team In G.Aviv+ K.Habad
42 | SCADA&Comm | 50 | 2020-12-07 | 21:00 | 5:00 | Pleshet Ring plastic tray installation all tracks | SCADA Vehicle Team in Pleshet all tracks
43 | SCADA&Comm | 50 | 2020-12-07 | 21:00 | 5:00 | Ashdod Ring plastic tray installation all tracks | SCADA Pedestrian Team In Ashdod
44 | TS | 50 | 2020-12-08 | 7:00 | 18:00 | construction | construction
45 | TS | 50 | 2020-12-08 | 7:00 | 18:00 | construction/electrical | construction/electrical
46 | TS | 50 | 2020-12-08 | 7:00 | 18:00 | construction | construction
47 | TS | 50 | 2020-12-08 | 7:00 | 18:00 | construction | construction
48 | TS | 50 | 2020-12-08 | 7:00 | 18:00 | construction | construction
49 | TS | 50 | 2020-12-08 | 7:00 | 18:00 | construction | construction
50 | OCS | 50 | 2020-12-08 | 7:00 | 19:00 | Foundation EP07 - Kp 86 until Kp 89 Track 1+2 | Foundation EP07 - Kp 86 until Kp 89 Track 1+2
51 | OCS | 50 | 2020-12-08 | 7:00 | 19:00 | Foundation EP07 - Kp 2 until Kp 6 Track 1+2 | Foundation Activity with vehicle on Track Kp 2 until Kp 6, Track 1+2
52 | OCS | 50 | 2020-12-08 | 8:00 | 17:00 | RW on in LOD Depot | OCS Vehicle Activity in LOD Depot
53 | OCS | 50 | 2020-12-08 | 8:00 | 17:00 | Install Cantilevers in LOD Depot | OCS Vehicle Activity in LOD Depot
54 | OCS | 50 | 2020-12-08 | 8:00 | 17:00 | Open platforms in Hod Hasharon & Kfar Sava stations (Working on the platforms) | Open platforms in Hod Hasharon & Kfar Sava stations (Working on the platforms)
55 | OCS-D | 50 | 2020-12-08 | 8:00 | 17:00 | Marking on EP05 on Kp 73-68, All Tracks | Marking on EP05 on Kp 73-68, All Tracks
56 | SCADA&Comm | 50 | 2020-12-08 | 8:00 | 18:00 | LOD Depot Ring plastic tray installation | SCADA Pedestrian Team In LOD Depot
57 | OCS | 50 | 2020-12-08 | 18:00 | 5:00 | Erect poles on Kp 113-118, (Out of the track) | Special Solutions in Kp 113-118, (Out of the track)
58 | OCS | 50 | 2020-12-08 | 18:00 | 20:00 | Preparation for Infrastructure Detection | Preparation for Infrastructure Detection
59 | OCS | 50 | 2020-12-08 | 19:00 | 5:00 | Foundation EP07 - Kp 2 until Kp 6 Track 1+2 | Foundation Activity with vehicle on Track Kp 2 until Kp 6, Track 1+2
60 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | Foundation EP08 - Kp 118 until Kp 130, Track 1+2 | Foundation Activity with vehicle on Track Kp 118 until Kp 130, Track 1+2
61 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | Foundations on Kp 106-108, Tracks 1&2 | Foundation Activity with vehicle in Kp 106-108, Tracks 1&2
62 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | E&B on Kp 11-12, Tracks 1&2 | OCS Pedestrian Activity on Kp 11-12, Tracks 1&2
63 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | Foundations on Kp 3-4, Tracks 2&3&4&5&6 | Foundation Activity with vehicle on Kp 3-4, Tracks 2&3&4&5&6
64 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | Adjustments on Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
65 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | Install Droppers on Kp 131-133, Track 2 | OCS Vehicle Activity Kp 131-133, Track 2
66 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | Wiring OCS on KP 140-135, Track 1 | OCS Vehicle Activity KP 140-135, Track 1
67 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | Install cantilevers on Kp 134, Tracks 1&2 | OCS Vehicle Activity Kp 131-133, Track 2
68 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | Install droppers and F.O Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
69 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | Install cantilevers on Kp 16-18, Tracks 1&2 | OCS Vehicle Activity Kp 16-18, Tracks 1&2
70 | OCS | 50 | 2020-12-08 | 21:00 | 5:00 | Install cantilevers on Kp10-14,Tracks 1&2 | OCS Vehicle Activity Kp10-14 Tracks 1&2
71 | SCADA&Comm | 50 | 2020-12-08 | 21:00 | 5:00 | Ganey Aviv+K.Habad Rings works | SCADA Pedestrian Team In G.Aviv+ K.Habad
72 | SCADA&Comm | 50 | 2020-12-08 | 21:00 | 5:00 | Pleshet Ring plastic tray installation all tracks | SCADA Vehicle Team in Pleshet all tracks
73 | SCADA&Comm | 50 | 2020-12-08 | 21:00 | 5:00 | Ashdod Ring plastic tray installation all tracks | SCADA Pedestrian Team In Ashdod
74 | TS | 50 | 2020-12-09 | 7:00 | 18:00 | construction | construction
75 | TS | 50 | 2020-12-09 | 7:00 | 18:00 | construction/electrical | construction/electrical
76 | TS | 50 | 2020-12-09 | 7:00 | 18:00 | construction | construction
77 | TS | 50 | 2020-12-09 | 7:00 | 18:00 | construction | construction
78 | TS | 50 | 2020-12-09 | 7:00 | 18:00 | construction | construction
79 | TS | 50 | 2020-12-09 | 7:00 | 18:00 | construction | construction
80 | OCS | 50 | 2020-12-09 | 7:00 | 19:00 | Foundation EP07 - Kp86 until Kp 89 Track 1+2 | Foundation EP07 - Kp86 until Kp 89 Track 1+2
81 | OCS | 50 | 2020-12-09 | 7:00 | 19:00 | Foundation EP07 - Kp 2 until Kp 6 Track 1+2 | Foundation Activity with vehicle on Track Kp 2 until Kp 6, Track 1+2
82 | OCS | 50 | 2020-12-09 | 8:00 | 17:00 | RW on in LOD Depot | OCS Vehicle Activity in LOD Depot
83 | OCS | 50 | 2020-12-09 | 8:00 | 17:00 | Install Cantilevers in LOD Depot | OCS Vehicle Activity in LOD Depot
84 | OCS | 50 | 2020-12-09 | 8:00 | 17:00 | Open platforms in Hod Hasharon & Kfar Sava stations (Working on the platforms) | Open platforms in Hod Hasharon & Kfar Sava stations (Working on the platforms)
85 | OCS-D | 50 | 2020-12-09 | 8:00 | 17:00 | Marking on EP05 on Kp 73-68, All Tracks | Marking on EP05 on Kp 73-68, All Tracks
86 | SCADA&Comm | 50 | 2020-12-09 | 8:00 | 18:00 | LOD Depot Ring plastic tray installation | SCADA Pedestrian Team In LOD Depot
87 | OCS | 50 | 2020-12-09 | 18:00 | 5:00 | Erect poles on Kp 113-118, (Out of the track) | Special Solutions in Kp 113-118, (Out of the track)
88 | OCS | 50 | 2020-12-09 | 18:00 | 20:00 | Preparation for Infrastructure Detection | Preparation for Infrastructure Detection
89 | OCS | 50 | 2020-12-09 | 19:00 | 5:00 | Foundation EP07 - Kp 2 until Kp 6 Track 1+2 | Foundation Activity with vehicle on Track Kp 2 until Kp 6, Track 1+2
90 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | Foundation EP08 - Kp 118 until Kp 130, Track 1+2 | Foundation Activity with vehicle on Track Kp 118 until Kp 130, Track 1+2
91 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | Foundations on Kp 106-108, Tracks 1&2 | Foundation Activity with vehicle in Kp 106-108, Tracks 1&2
92 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | E&B on Kp 11-12, Tracks 1&2 | OCS Pedestrian Activity on Kp 11-12, Tracks 1&2
93 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | Foundations on Kp 3-4, Tracks 2&3&4&5&6 | Foundation Activity with vehicle on Kp 3-4, Tracks 2&3&4&5&6
94 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | Adjustments on Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
95 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | Install Droppers on Kp 131-133, Track 2 | OCS Vehicle Activity Kp 131-133, Track 2
96 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | Wiring OCS on KP 140-135, Track 1 | OCS Vehicle Activity KP 140-135, Track 1
97 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | Install cantilevers on Kp 134, Tracks 1&2 | OCS Vehicle Activity Kp 131-133, Track 2
98 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | Install droppers and F.O Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
99 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | Install cantilevers on Kp 16-18, Tracks 1&2 | OCS Vehicle Activity Kp 16-18, Tracks 1&2
100 | OCS | 50 | 2020-12-09 | 21:00 | 5:00 | Install RW on Kp 15-18, Tracks 1&2 | OCS Vehicle Activity Kp 15-18, Tracks 1&2
101 | SCADA&Comm | 50 | 2020-12-09 | 21:00 | 5:00 | Ganey Aviv+K.Habad Rings works | SCADA Pedestrian Team In G.Aviv+ K.Habad
102 | SCADA&Comm | 50 | 2020-12-09 | 21:00 | 5:00 | Pleshet Ring plastic tray installation all tracks | SCADA Vehicle Team in Pleshet all tracks
103 | SCADA&Comm | 50 | 2020-12-09 | 21:00 | 5:00 | Ashdod Ring plastic tray installation all tracks | SCADA Pedestrian Team In Ashdod
104 | TS | 50 | 2020-12-10 | 7:00 | 18:00 | construction | construction
105 | TS | 50 | 2020-12-10 | 7:00 | 18:00 | construction/electrical | construction/electrical
106 | TS | 50 | 2020-12-10 | 7:00 | 18:00 | construction | construction
107 | TS | 50 | 2020-12-10 | 7:00 | 18:00 | construction | construction
108 | TS | 50 | 2020-12-10 | 7:00 | 18:00 | construction | construction
109 | TS | 50 | 2020-12-10 | 7:00 | 18:00 | construction | construction
110 | OCS | 50 | 2020-12-10 | 7:00 | 19:00 | Foundation EP07 - Kp86 until Kp 89 Track 1+2 | Foundation EP07 - Kp86 until Kp 89 Track 1+2
111 | OCS | 50 | 2020-12-10 | 7:00 | 19:00 | Foundation EP07 - Kp 2 until Kp 6 Track 1+2 | Foundation Activity with vehicle on Track Kp 2 until Kp 6, Track 1+2
112 | OCS | 50 | 2020-12-10 | 8:00 | 17:00 | RW on in LOD Depot | OCS Vehicle Activity in LOD Depot
113 | OCS | 50 | 2020-12-10 | 8:00 | 17:00 | Install Cantilevers in LOD Depot | OCS Vehicle Activity in LOD Depot
114 | OCS | 50 | 2020-12-10 | 8:00 | 17:00 | Open platforms in Hod Hasharon & Kfar Sava stations (Working on the platforms) | Open platforms in Hod Hasharon & Kfar Sava stations (Working on the platforms)
115 | OCS-D | 50 | 2020-12-10 | 8:00 | 17:00 | Marking on EP05 on Kp 73-68, All Tracks | Marking on EP05 on Kp 73-68, All Tracks
116 | SCADA&Comm | 50 | 2020-12-10 | 8:00 | 18:00 | LOD Depot Ring plastic tray installation | SCADA Pedestrian Team In LOD Depot
117 | OCS | 50 | 2020-12-10 | 19:00 | 5:00 | Foundation EP07 - Kp 2 until Kp 6 Track 1+2 | Foundation Activity with vehicle on Track Kp 2 until Kp 6, Track 1+2
118 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | Foundation EP08 - Kp 118 until Kp 130, Track 1+2 | Foundation Activity with vehicle on Track Kp 118 until Kp 130, Track 1+2
119 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | Foundations on Kp 106-108, Tracks 1&2 | Foundation Activity with vehicle in Kp 106-108, Tracks 1&2
120 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | E&B on Kp 153, All Tracks | OCS Pedestrian Activity on Kp 153, All Tracks
121 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | Foundations on Kp 90-2, Tracks 1&2 | Foundation Activity with vehicle on Kp 90-2, Tracks 1&2
122 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | Adjustments on Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
123 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | Install Droppers on Kp 131-133, Track 2 | OCS Vehicle Activity Kp 131-133, Track 2
124 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | Wiring OCS on KP 140-135, Track 1 | OCS Vehicle Activity KP 140-135, Track 1
125 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | Install cantilevers on Kp 134, Tracks 1&2 | OCS Vehicle Activity Kp 131-133, Track 2
126 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | Install droppers and F.O Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
127 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | Install cantilevers on Kp 16-18, Tracks 1&2 | OCS Vehicle Activity Kp 16-18, Tracks 1&2
128 | OCS | 50 | 2020-12-10 | 21:00 | 5:00 | Install RW on Kp 15-18, Tracks 1&2 | OCS Vehicle Activity Kp 15-18, Tracks 1&2
129 | SCADA&Comm | 50 | 2020-12-10 | 21:00 | 5:00 | Ganey Aviv+K.Habad Rings works | SCADA Pedestrian Team In G.Aviv+ K.Habad
130 | SCADA&Comm | 50 | 2020-12-10 | 21:00 | 5:00 | Pleshet Ring plastic tray installation all tracks | SCADA Vehicle Team in Pleshet all tracks
131 | SCADA&Comm | 50 | 2020-12-10 | 21:00 | 5:00 | Ashdod Ring plastic tray installation all tracks | SCADA Pedestrian Team In Ashdod
132 | OCS | 50 | 2020-12-11 | 7:00 | 19:00 | Foundation EP07 - Kp 2 until Kp 6 Track 1+2 | Foundation Activity with vehicle on Track Kp 2 until Kp 6, Track 1+2
133 | OCS | 50 | 2020-12-11 | 7:00 | 19:00 | Foundation EP14 - Kp152 until Kp 154+600, Track 3+4 | Foundation Activity with vehicle on Track Kp 152 until Kp 154+600, Track 3+4
134 | OCS | 50 | 2020-12-11 | 8:00 | 17:00 | RW on in LOD Depot | OCS Vehicle Activity in LOD Depot
135 | OCS | 50 | 2020-12-11 | 8:00 | 17:00 | Install Cantilevers in LOD Depot | OCS Vehicle Activity in LOD Depot
136 | OCS | 50 | 2020-12-11 | 8:00 | 17:00 | Erect poles on Kp 113-118, (Out of the track) | Special Solutions in Kp 113-118, (Out of the track)
137 | OCS | 50 | 2020-12-11 | 15:00 | 23:00 | E&B on Kp 153, All Tracks | OCS Pedestrian Activity on Kp 153, All Tracks
138 | OCS | 50 | 2020-12-11 | 15:00 | 23:00 | Foundations on Kp 106-108, Tracks 1&2 | Foundation Activity with vehicle in Kp 106-108, Tracks 1&2
139 | OCS | 50 | 2020-12-11 | 19:00 | 5:00 | Foundation EP14 - Kp 118 until Kp 130, Track 1+2 | Foundation Activity with vehicle on Track Kp 118 until Kp 130, Track 1+2
140 | OCS | 50 | 2020-12-11 | 19:00 | 5:00 | Foundation EP08 - Kp 152 until Kp 154+600, Track 3+4 | Foundation Activity with vehicle on Track Kp 152 until Kp 154+600, Track 3+4
141 | OCS | 50 | 2020-12-11 | 21:00 | 6:00 | Foundations on Kp 90-2, Tracks 1&2 | Foundation Activity with vehicle on Kp 90-2, Tracks 1&2
142 | OCS | 50 | 2020-12-11 | 21:00 | 5:00 | Adjustments on Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
143 | OCS | 50 | 2020-12-11 | 21:00 | 5:00 | Install droppers on Kp 140-133, All Tracks | OCS Vehicle Activity Kp 140-133, All Tracks
144 | OCS | 50 | 2020-12-11 | 21:00 | 5:00 | Distribute materials on Kp 131-134 (Out of the track) | OCS Vehicle Activity Kp 131-134 (Out of the track)
145 | OCS | 50 | 2020-12-11 | 21:00 | 5:00 | Wiring OCS KP 134, Track 2 | OCS Vehicle Activity KP 134, Track 2
146 | OCS | 50 | 2020-12-11 | 21:00 | 5:00 | Install droppers on Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
147 | OCS | 50 | 2020-12-11 | 21:00 | 6:00 | Erect poles and RW on Kp 18-10, Track 1&2&3 | OCS Vehicle Activity Kp 18-10, Track 1&2&3
148 | OCS | 50 | 2020-12-11 | 21:00 | 6:00 | Erect poles and RW on Kp 18-10, Track 1&2&3 | OCS Vehicle Activity Kp 18-10, Track 1&2&3
149 | OCS | 50 | 2020-12-12 | 7:00 | 19:00 | Foundation EP07 - Kp 2 until Kp 6 Track 1+2 | Foundation Activity with vehicle on Track Kp 2 until Kp 6, Track 1+2
150 | OCS | 50 | 2020-12-12 | 7:00 | 19:00 | Foundation EP14 - Kp 152 until Kp 154+600, Track 3+4 | Foundation Activity with vehicle on Track Kp 152 until Kp 154+600, Track 3+4
151 | OCS | 50 | 2020-12-12 | 8:00 | 17:00 | RW on in LOD Depot | OCS Vehicle Activity in LOD Depot
152 | OCS | 50 | 2020-12-12 | 8:00 | 17:00 | Install Cantilevers in LOD Depot | OCS Vehicle Activity in LOD Depot
153 | OCS | 50 | 2020-12-12 | 8:00 | 17:00 | Foundations on Kp 106-108, Tracks 1&2 | Foundation Activity with vehicle in Kp 106-108, Tracks 1&2
154 | OCS | 50 | 2020-12-12 | 8:00 | 17:00 | E&B on Kp 153, All Tracks | OCS Pedestrian Activity on Kp 153, All Tracks
155 | OCS | 50 | 2020-12-12 | 8:00 | 17:00 | Erect poles on Kp 113-118, (Out of the track) | Special Solutions in Kp 113-118, (Out of the track)
156 | OCS-D | 50 | 2020-12-12 | 8:00 | 17:00 | Marking on EP05 on Kp 73-68, All Tracks | Marking on EP05 on Kp 73-68, All Tracks
157 | OCS | 50 | 2020-12-12 | 21:00 | 5:00 | Foundation EP08 - Kp 118 until Kp 130, Track 1+2 | Foundation Activity with vehicle on Track Kp 118 until Kp 130, Track 1+2
158 | OCS | 50 | 2020-12-12 | 21:00 | 5:00 | Foundations on Kp 90-2, Tracks 1&2 | Foundation Activity with vehicle on Kp 90-2, Tracks 1&2
159 | OCS | 50 | 2020-12-12 | 21:00 | 5:00 | Install droppers on Kp 140-133, All Tracks | OCS Vehicle Activity Kp 140-133, All Tracks
160 | OCS | 50 | 2020-12-12 | 21:00 | 5:00 | Distribute materials on Kp 131-134 (Out of the track) | OCS Vehicle Activity Kp 131-134 (Out of the track)
161 | OCS | 50 | 2020-12-12 | 21:00 | 5:00 | Wiring OCS KP 134, Track 2 | OCS Vehicle Activity KP 134, Track 2
162 | OCS | 50 | 2020-12-12 | 21:00 | 5:00 | Install droppers on Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
163 | OCS | 50 | 2020-12-12 | 21:00 | 5:00 | Adjustments on Kp 134-140, Track 2 | OCS Vehicle Activity Kp 134-140, Track 2
164 | OCS | 50 | 2020-12-12 | 21:00 | 5:00 | Erect poles and RW on Kp 18-10, Track 1&2&3 | OCS Vehicle Activity Kp 18-10, Track 1&2&3
165 | OCS | 50 | 2020-12-12 | 21:00 | 5:00 | Erect poles and RW on Kp 18-10, Track 1&2&3 | OCS Vehicle Activity Kp 18-10, Track 1&2&3
Night works
Morning works