## Weekend Plan
WW06 Construction Work Plan 03-09.02.19 V0.1
Row # | Discipline [OCS/Old Bridges/TS/SCADA & COM] | WW [Nº] | Date [DD/MM/YY] | T.P Start [Time] | T.P End [Time] | Work Description
1 | TS | 6 | 2019-02-03 | 7:00 | 18:00 | construction
2 | TS | 6 | 2019-02-03 | 7:00 | 18:00 | construction/electrical
3 | TS | 6 | 2019-02-03 | 7:00 | 18:00 | construction
4 | TS | 6 | 2019-02-03 | 7:00 | 18:00 | construction
5 | TS | 6 | 2019-02-03 | 7:00 | 18:00 | construction
6 | OCS | 6 | 2019-02-03 | 7:00 | 15:00 | Infrastructure detection Lod Curve (No need Track Possession)
7 | TS+SCADA | 6 | 2019-02-03 | 8:00 | 16:00 | Utility Detection and Site Tour in Holtz (SCADA +TS), kp 97+500 - 98+800
8 | OCS | 6 | 2019-02-03 | 21:00 | 4:30 | Disconnectors and E&B works in EP11 kp 20-23, track 1&2
9 | OCS | 6 | 2019-02-03 | 21:00 | 4:30 | WT Installation Kp 97, track 3 and Track 4 ID: 97.4.12,15,11,10,9,8
10 | OCS | 6 | 2019-02-03 | 21:00 | 4:30 | Installing Boltz and Drilling special solutions on Ayalon Wall (River side) track 3
11 | OCS | 6 | 2019-02-03 | 21:00 | 4:30 | Disconnector Holtz kp 4-7 track 1&2
12 | OCS | 6 | 2019-02-03 | 21:00 | 4:30 | Foundations Works EP06 kp 95-94, track 1
13 | SCADA & COM | 6 | 2019-02-03 | 21:00 | 4:30 | Mishmar - Testing , Kp 20+800 - 25+300
14 | SCADA & COM | 6 | 2019-02-03 | 21:00 | 4:30 | NatBag Cable Deployment , kp 7+600 - 5+050 Track 1&2 + (ISR cable duct exposure) integrated Supervisor
15 | SCADA & COM | 6 | 2019-02-03 | 21:00 | 4:30 | Daniel Motors Connection , kp 16+700 - 18+220 Track 1&2
16 | SCADA & COM | 6 | 2019-02-03 | 21:00 | 4:30 | LOP internal test for As Made
17 | TS | 6 | 2019-02-04 | 7:00 | 18:00 | construction
18 | TS | 6 | 2019-02-04 | 7:00 | 18:00 | construction/electrical
19 | TS | 6 | 2019-02-04 | 7:00 | 18:00 | construction
20 | TS | 6 | 2019-02-04 | 7:00 | 18:00 | construction
21 | TS | 6 | 2019-02-04 | 7:00 | 18:00 | construction
22 | OCS | 6 | 2019-02-04 | 21:00 | 4:30 | Disconnectors and E&B works in EP11 kp 4-7, track 1&2
23 | OCS | 6 | 2019-02-04 | 21:00 | 4:30 | Drillings Specials solutions kp 95
24 | OCS | 6 | 2019-02-04 | 21:00 | 4:30 | WT Installation Kp 97, track 3 and Track 4 ID: 97-4.12,15,11,10,9,8
25 | OCS | 6 | 2019-02-04 | 21:00 | 4:30 | Installing Boltz and Drilling special solutions on Ayalon Wall (River side) track 3
26 | OCS | 6 | 2019-02-04 | 21:00 | 4:30 | WT Installation Kp 97, track 3 and Track 4 ID: 97-4.12,15,11,10,9,8
27 | OCS | 6 | 2019-02-04 | 21:00 | 4:30 | EB works EP11 Daniel's tunnels kp 17-19, track 1&2
28 | OCS | 6 | 2019-02-04 | 21:00 | 4:30 | Disconnectors and E&B works in EP11 kp 20-23, track 1&2
29 | OCS | 6 | 2019-02-04 | 21:00 | 4:30 | Surveyor track 3, kp 94-97
30 | OCS | 6 | 2019-02-04 | 21:00 | 4:30 | Specials Solutions track 1, kp 98-96 ID: 97-1.03, 97-1.01, 96-1.21bis, 96-1.21, 96-1.19, 96-1.18
31 | OCS | 6 | 2019-02-04 | 21:00 | 4:30 | Disconnector Installation kp 4-19, track 2
32 | SCADA & COM | 6 | 2019-02-04 | 21:00 | 4:30 | Mishmar - Testing , Kp 20+800 - 25+300
33 | SCADA & COM | 6 | 2019-02-04 | 21:00 | 4:30 | NatBag Cable Deployment , kp 7+600 - 5+050 Track 1&2 + (ISR cable duct exposure) integrated Supervisor
34 | SCADA & COM | 6 | 2019-02-04 | 21:00 | 4:30 | Daniel Motors Connection , kp 16+700 - 18+220 Track 1&2
35 | TS | 6 | 2019-02-05 | 7:00 | 18:00 | construction
36 | TS | 6 | 2019-02-05 | 7:00 | 18:00 | construction/electrical
37 | TS | 6 | 2019-02-05 | 7:00 | 18:00 | construction
38 | TS | 6 | 2019-02-05 | 7:00 | 18:00 | construction
39 | TS | 6 | 2019-02-05 | 7:00 | 18:00 | construction
40 | SCADA & COM | 6 | 2019-02-05 | 9:00 | 17:00 | Daniel LOP connection to ISR SHOB fire system
41 | OCS | 6 | 2019-02-05 | 21:00 | 4:30 | Disconnectors and E&B works in EP11 kp 4-7, track 1&2
42 | OCS | 6 | 2019-02-05 | 21:00 | 4:30 | Drillings Specials solutions kp 95
43 | OCS | 6 | 2019-02-05 | 21:00 | 4:30 | WT Installation Kp 97, track 3 and Track 4 ID: 97.4.12,15,11,10,9,8
44 | OCS | 6 | 2019-02-05 | 21:00 | 4:30 | Installing Boltz and Drilling special solutions on Ayalon Wall (River side) track 3
45 | OCS | 6 | 2019-02-05 | 21:00 | 4:30 | Surveyor track 3&4, kp 98-97
46 | OCS | 6 | 2019-02-05 | 21:00 | 4:30 | WT Installation Kp 97, track 3 and Track 4 ID: 97.4.12,15,11,10,9,8
47 | OCS | 6 | 2019-02-05 | 21:00 | 4:30 | EB works EP09 Kp 0-3, track 1
48 | OCS | 6 | 2019-02-05 | 21:00 | 4:30 | Disconnectors and E&B works in EP11 kp 20-23, track 1&2
49 | OCS | 6 | 2019-02-05 | 21:00 | 4:30 | Disconnector Installation kp 4-19, track 2
50 | OCS | 6 | 2019-02-05 | 22:00 | 4:30 | Site tour kp 94+875- 95+156 track 3, ID: 94-3.22, 94-3.23, 94-3.24, 95-3.02, 95-3.04
51 | OCS | 6 | 2019-02-05 | 21:00 | 4:30 | Specials Solutions track 1, kp 98-96 ID: 97-1.03, 97-1.01, 96-1.21bis, 96-1.21, 96-1.19, 96-1.18
52 | SCADA & COM | 6 | 2019-02-05 | 21:00 | 4:30 | Mishmar - Testing , Kp 20+800 - 25+300
53 | SCADA & COM | 6 | 2019-02-05 | 21:00 | 4:30 | NatBag Cable Deployment , kp 7+600 - 5+050 Track 1&2 + (ISR cable duct exposure) integrated Supervisor
54 | SCADA & COM | 6 | 2019-02-05 | 21:00 | 4:30 | Daniel Motors Connection , kp 16+700 - 18+220 Track 1&2
55 | TS | 6 | 2019-02-06 | 7:00 | 18:00 | construction
56 | TS | 6 | 2019-02-06 | 7:00 | 18:00 | construction/electrical
57 | TS | 6 | 2019-02-06 | 7:00 | 18:00 | construction
58 | TS | 6 | 2019-02-06 | 7:00 | 18:00 | construction
59 | TS | 6 | 2019-02-06 | 7:00 | 18:00 | construction
60 | SCADA & COM | 6 | 2019-02-06 | 21:00 | 4:30 | Mishmar - Testing , Kp 20+800 - 25+300
61 | SCADA & COM | 6 | 2019-02-06 | 21:00 | 4:30 | NatBag Cable Deployment , kp 7+600 - 5+050 Track 1&2 + (ISR cable duct exposure) integrated Supervisor
62 | SCADA & COM | 6 | 2019-02-06 | 21:00 | 4:30 | Daniel Motors Connection , kp 16+700 - 18+220 Track 1&2
63 | SCADA & COM | 6 | 2019-02-06 | 21:00 | 4:30 | LOP internal test for As Made
64 | OCS | 6 | 2019-02-06 | 21:00 | 4:30 | Disconnectors and E&B works in EP11 kp 4-7, track 1&2
65 | OCS | 6 | 2019-02-06 | 21:00 | 4:30 | WT Installation Kp 97, track 3 and Track 4 ID: 97.4.12,15,11,10,9,8
66 | OCS | 6 | 2019-02-06 | 21:00 | 4:30 | Drilling & Bolts Installation special solutions on Ayalon Wall (River side) track 3, kp 94-96
67 | OCS | 6 | 2019-02-06 | 21:00 | 4:30 | Drillings Specials solutions kp 95
68 | OCS | 6 | 2019-02-06 | 21:00 | 4:30 | WT Installation Kp 97, track 3 97.4.12,15,11,10,9,8
69 | OCS | 6 | 2019-02-06 | 21:00 | 4:30 | EB works EP09 Connections Earthing System with the bridge 9&10, kp 19-15
70 | OCS | 6 | 2019-02-06 | 21:00 | 4:30 | Disconnectors and E&B works in EP11 kp 20-23, track 1&2
71 | OCS | 6 | 2019-02-06 | 21:00 | 4:30 | Specials Solutions track 1, kp 98-96 ID: 97-1.03, 97-1.01, 96-1.21bis, 96-1.21, 96-1.19, 96-1.18
72 | OCS | 6 | 2019-02-06 | 21:00 | 4:30 | Adjustments track 2, kp 6-12
73 | TS | 6 | 2019-02-07 | 7:00 | 18:00 | construction
74 | TS | 6 | 2019-02-07 | 7:00 | 18:00 | construction/electrical
75 | TS | 6 | 2019-02-07 | 7:00 | 18:00 | construction
76 | TS | 6 | 2019-02-07 | 7:00 | 18:00 | construction
77 | TS | 6 | 2019-02-07 | 7:00 | 18:00 | construction
78 | OCS | 6 | 2019-02-07 | 21:00 | 6:00 | Disconnectors and E&B works in EP11 kp 4-7, track 1&2
79 | OCS | 6 | 2019-02-07 | 21:00 | 6:00 | Erecting Poles on Kp 97, track 3 and Track 4 ID: 97.4.12,15,11,10,9,8
80 | OCS | 6 | 2019-02-07 | 21:00 | 6:00 | Droppers& Stitch Wire Track 1ת kp 97
81 | OCS | 6 | 2019-02-07 | 0:00 | 6:00 | Wiring track 1, Kp 98 ID: 98.1.4.Bis-98.1.20
82 | OCS | 6 | 2019-02-07 | 1:00 | 10:00 | Foundations Works EP06 kp 95-94, track 1
83 | OCS | 6 | 2019-02-07 | 21:00 | 6:00 | E&B Works in EP09 in Hagana Station
84 | OCS | 6 | 2019-02-07 | 21:00 | 5:00 | Specials Solutions track 1, kp 98-96 ID: 97-1.03, 97-1.01, 96-1.21bis, 96-1.21, 96-1.19, 96-1.18
85 | OCS | 6 | 2019-02-07 | 21:00 | 6:00 | Disconnectors and E&B works in EP11 kp 20-27, track 1&2
86 | OCS | 6 | 2019-02-07 | 21:00 | 6:00 | Adjustments track 1 kp 6-12
87 | OCS | 6 | 2019-02-07 | 21:00 | 5:00 | Frame work kp 94+875- 95+156 track 3, ID: 94-3.22, 94-3.23, 94-3.24, 95-3.02, 95-3.04
88 | OCS | 5 | 2019-02-07 | 23:59 | 7:00 | Fixing the fence between KP 96 - 96+650 near track 2 (including SPIS track vehicle) and installing fence between track 1 and track 2 from kp 94 -93(SPIS Vehicle will move on track 1) + MATAV Surveyor
89 | SCADA & COM | 6 | 2019-02-07 | 21:00 | 6:00 | Mishmar - Testing , Kp 20+800 - 25+300
90 | SCADA & COM | 6 | 2019-02-07 | 21:00 | 6:00 | NatBag Cable Deployment , kp 7+600 - 5+050 Track 1&2 + (ISR cable duct exposure) integrated Supervisor
91 | SCADA & COM | 6 | 2019-02-07 | 21:00 | 6:00 | Daniel Motors Connection , kp 16+700 - 18+220 Track 1&2
92 | SCADA & COM | 6 | 2019-02-07 | 23:59 | 9:00 | TLV South SCADA ring Excavetion+Metal Tray installation 5+537 till 96+300
93 | SCADA & COM | 6 | 2019-02-07 | 21:00 | 6:00 | Shapirim Cable Deployment including Track Vehicle in Track 2 + ISR Cable duct exposure in track 2 - Kp 4+668 (700m Before Natbag Station) to Kp 7+897 (Ganot NS)
94 | TS | 6 | 2019-02-08 | 7:00 | 12:00 | construction
95 | TS | 6 | 2019-02-08 | 7:00 | 12:00 | construction/electrical
96 | TS | 6 | 2019-02-08 | 7:00 | 12:00 | construction
97 | TS | 6 | 2019-02-08 | 7:00 | 12:00 | construction
98 | TS | 6 | 2019-02-08 | 7:00 | 12:00 | construction
99 | OCS | 6 | 2019-02-08 | 5:00 | 18:00 | Frame work kp 94+875- 95+156 track 3, ID: 94-3.22, 94-3.23, 94-3.24, 95-3.02, 95-3.04
100 | OCS | 6 | 2019-02-08 | 8:00 | 15:00 | Mapping Tracks kp 94-92, Track 2,3,1
101 | OCS | 6 | 2019-02-08 | 5:00 | 13:00 | Specials Solutions track 1, kp 98-96 ID: 97-1.03, 97-1.01, 96-1.21bis, 96-1.21, 96-1.19, 96-1.18
102 | SCADA & COM | 6 | 2019-02-08 | 8:00 | 17:00 | NatBag Cable Deployment , kp 7+600 - 5+050 Track 1&2 + (ISR cable duct exposure) integrated Supervisor
103 | SCADA & COM | 6 | 2019-02-08 | 9:00 | 18:00 | TLV South SCADA ring Excavetion+Metal Tray installation 5+537 till 96+300
104 | SCADA & COM | 6 | 2019-02-08 | 6:00 | 15:00 | Shapirim Cable Deployment including Track Vehicle in Track 2 + ISR Cable duct exposure in track 2 - Kp 4+668 (700m Before Natbag Station) to Kp 7+897 (Ganot NS)
105 | SCADA & COM | 6 | 2019-02-08 | 15:00 | 23:59 | Shapirim Cable Deployment including Track Vehicle in Track 2 + ISR Cable duct exposure in track 2 - Kp 4+668 (700m Before Natbag Station) to Kp 7+897 (Ganot NS)
106 | OCS | 6 | 2019-02-08 | 15:00 | 23:59 | Wiring track 1, Kp 98 ID:98.1.4.Bis-98.1.20
107 | OCS | 6 | 2019-02-08 | 15:00 | 23:59 | Adjustments track 2, Kp 99-5
108 | OCS | 6 | 2019-02-08 | 15:00 | 23:59 | Droppers& Stitch Wire Track 1, kp 97
109 | OCS | 6 | 2019-02-08 | 15:00 | 23:59 | EB works in EP 11 on Bridge 7-8-9-10 kp 5-20, Track 1&2 and kp 0 track 1&2
110 | OCS | 6 | 2019-02-08 | 15:00 | 23:59 | Erecting Poles LOD Curve
111 | OCS | 5 | 2019-02-08 | 15:00 | 23:59 | Disconnectors and E&B works in EP11 kp 20-27, track 1&2
112 | OCS | 5 | 2019-02-08 | 15:00 | 23:59 | Adjustments kp 99-5, track 2
113 | SCADA & COM | 6 | 2019-02-08 | 18:00 | 3:00 | TLV South SCADA ring Excavetion+Metal Tray installation 5+537 till 96+300
114 | OCS | 5 | 2019-02-08 | 17:00 | 5:00 | Fixing the fence between KP 96 - 96+650 near track 2 (including SPIS track vehicle) and installing fence between track 1 and track 2 from kp 94 -93(SPIS Vehicle will move on track 1) + MATAV Surveyor
115 | OCS | 5 | 2019-02-08 | 18:00 | 5:00 | Frame work kp 94+875- 95+156 track 3, ID: 94-3.22, 94-3.23, 94-3.24, 95-3.02, 95-3.04
116 | SCADA & COM | 6 | 2019-02-08 | 23:59 | 9:00 | Shapirim Cable Deployment including Track Vehicle in Track 2 + ISR Cable duct exposure in track 2 - Kp 4+668 (700m Before Natbag Station) to Kp 7+897 (Ganot NS)
117 | OCS | 5 | 2019-02-09 | 8:00 | 15:00 | Wiring track 1, Kp 98 ID: 98.1.4.Bis-98.1.20
118 | OCS | 5 | 2019-02-09 | 8:00 | 15:00 | Adjustments track 2, Kp 0-5
119 | OCS | 5 | 2019-02-09 | 8:00 | 15:00 | EB works in EP 11 on Bridge 7-8-9-10 kp 5-20, Track 1&2 and kp 0 track 1&2
120 | OCS | 5 | 2019-02-09 | 8:00 | 15:00 | Droppers& Stitch Wire Track 1 kp 97
121 | OCS | 5 | 2019-02-09 | 8:00 | 15:00 | Erecting Poles LOD Curve
122 | OCS | 5 | 2019-02-09 | 8:00 | 15:00 | Disconnectors and E&B works in EP11 kp 20-23, track 1&2
123 | OCS | 5 | 2019-02-09 | 8:00 | 15:00 | Adjustments track 2 from Kp 98 to 5
124 | OCS | 5 | 2019-02-09 | 6:30 | 14:00 | CASTING 3 ELEMNTS ON PLATFORM NO' 5 / Remove the frame on the elements on track 1 kp 97
125 | OCS | 5 | 2019-02-09 | 8:00 | 15:00 | Mapping Tracks kp 97-94, Track 2&3
126 | OCS | 5 | 2019-02-09 | 5:00 | 15:00 | Frame work kp 94+875- 95+156 track 3, ID: 94-3.22, 94-3.23, 94-3.24, 95-3.02, 95-3.04
127 | SCADA & COM | 6 | 2019-02-09 | 3:00 | 12:00 | TLV South SCADA ring Excavetion+Metal Tray installation 5+537 till 96+300
128 | SCADA & COM | 6 | 2019-02-09 | 12:00 | 17:00 | TLV South SCADA ring Excavetion+Metal Tray installation 5+537 till 96+300
129 | SCADA & COM | 6 | 2019-02-09 | 9:00 | 17:00 | Shapirim Cable Deployment including Track Vehicle in Track 2 + ISR Cable duct exposure in track 2 - Kp 4+668 (700m Before Natbag Station) to Kp 7+897 (Ganot NS)
Night works
Morning works